## Work Breakdown Structure
[6 empty] | Total | Done | Open | Not Open | Start Over |  | Finish Over |  |  | 2018-08-01 | [60 empty] | 5% |  |  | 5% |  |  | 10% |  |  | 10% |  |  | 10% |  |  | 5% |  |  | 5% |  |  | 10% |  |  | 5% |  |  | 5% |  |  | 5% |  |  | 10% |  |  | 5% |  |  | 5% | [24 empty] | Date： 2018/08/01
XÂY DỰNG MOBILE APP BÁN TRANG SỨC ONLINE | [5 empty] | 100 | 70 | 0 | 0 | 0 |  | 0 | [63 empty] | Nghiệp vụ |  |  | Phân tích |  |  | Database |  |  | UI |  |  | service |  |  | Catelogy |  |  | Login |  |  | Cart |  |  | List product |  |  | Login system |  |  | Manager User |  |  | Manager cart |  |  | Tối ưu |  |  | Setup | [24 empty] | 0
Summary Information
[6 empty] | 2018-07-01 | 2018-10-01 | 2018-06-25 | 2018-06-27 | 0 |  | 0 |  |  |  | 2018 | 7 | [30 empty] | 8 | [30 empty] | 9 | [29 empty] | 10 | [30 empty] | Note
Category | SubCategory | No | Task/Function | SubTask/SubFuntion | Phụ trách | Plan |  | Actual |  | Cost Plan |  | Cost Actual |  | Status | Progress | time axis 2018-07-01 to 2018-10-31
[6 empty] | Start | Finish | Start | Finish | Hours | Days | Hours | Days | time axis 2018-07-01 to 2018-10-31
Tìm hiểu | React-native |  | Props |  |  | 2018-07-01 | 2018-07-09 | 2018-06-25 | 2018-06-27 |  |  |  |  | Xong | 5 | 5
|  |  | State |  |  | 2018-07-01 | 2018-07-09 | 2018-06-26 | 2018-06-29 |  |  |  |  | Xong
|  |  | Component |  |  | 2018-07-01 | 2018-07-09 | 2018-06-29 | 2018-07-02 |  |  |  |  | Xong
|  |  | Construction |  |  | 2018-07-01 | 2018-07-09 | 2018-07-02 | 2018-07-07 |  |  |  |  | Xong
|  |  | Destruction |  |  | 2018-07-01 | 2018-07-09 | 2018-07-02 | 2018-07-07 |  |  |  |  | Xong
| Môi trường |  | Cài đặt | NodeJS |  | 2018-07-03 | 2018-07-05 | 2018-07-03 | 2018-07-05 |  |  |  |  | Xong
|  |  |  | Android Studio |  | 2018-07-03 | 2018-07-05 | 2018-07-03 | 2018-07-05 |  |  |  |  | Xong
|  |  |  | Genymotion |  | 2018-07-03 | 2018-07-05 | 2018-07-03 | 2018-07-05 |  |  |  |  | Xong
|  |  |  | React native |  | 2018-07-03 | 2018-07-05 | 2018-07-03 | 2018-07-05 |  |  |  |  | Xong
Phân tích | Chức năng |  | Người dùng | Danh mục sản phẩm |  | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 |  |  |  |  | Xong | 5 | 5
|  |  |  | Sản phẩm bán chạy |  | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
|  |  |  | Tìm kiếm sản phẩm |  | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
|  |  |  | Mua hàng |  | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
|  |  |  | Login/sign up |  | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
|  |  | Admin | Quản lí sản phẩm |  | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 |  |  |  |  | Xong
|  |  |  | Quản lí đơn hàng |  | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
|  |  |  | Quản lí người dùng |  | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
| Phác thảo UI |  | Người dùng |  |  | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 |  |  |  |  | Xong
|  |  | Admin |  |  | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
Thiết kế | Database |  | Tạo database |  |  | 2018-07-07 | 2018-07-08 | 2018-07-07 | 2018-07-09 |  |  |  |  | Xong | 10 | 10
|  |  | Tạo dữ liệu |  |  | 2018-07-10 | 2018-07-10 | 2018-07-12 | 2018-07-12 |  |  |  |  | Xong
| Giao diện |  |  |  |  | 2018-07-10 | 2018-07-13 | 2018-07-13 | 2018-07-14 | [5 empty] | 10 | 5
Coding | Service |  | Tìm hiểu laravel | Route |  | 2018-07-13 | 2018-07-15 | 2018-07-14 | 2018-07-16 |  |  |  |  | Xong | 10 | 7
|  |  |  | Migrate |  | 2018-07-13 | 2018-07-15 | 2018-07-14 | 2018-07-16 |  |  |  |  | Xong
|  |  |  | Model |  | 2018-07-13 | 2018-07-15 | 2018-07-14 | 2018-07-16 |  |  |  |  | Xong
|  |  |  | RestfullController |  | 2018-07-13 | 2018-07-15 | 2018-07-14 | 2018-07-16 |  |  |  |  | Xong
|  |  | Connect DB |  |  | 2018-07-14 | 2018-07-15 | 2018-07-14 | 2018-07-16 |  |  |  |  | Xong
|  |  | Tạo API | getAllProductType |  | 2018-07-14 | 2018-07-16 | 2018-07-14 | 2018-07-16 |  |  |  |  | Xong
|  |  |  | getAllProduct |  | 2018-07-14 | 2018-07-16 | 2018-07-14 | 2018-07-16 |  |  |  |  | Xong
|  |  |  | getAllCustomer |  | 2018-07-14 | 2018-07-16 | 2018-07-14 | 2018-07-16 |  |  |  |  | Xong
|  |  |  | getListProduct |  | 2018-07-15 | 2018-07-16 | 2018-07-17 | 2018-07-17
|  |  |  | searchProduct |  | 2018-07-16 | 2018-07-16 | 2018-07-17 | 2018-07-17
| React native |  | navigator |  |  | 2018-07-17 | 2018-07-18 | 2018-07-18 | 2018-07-19
|  |  | drawer |  |  | 2018-07-18 | 2018-07-19 | 2018-07-19 | 2018-07-20
|  |  | fetch |  |  | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22
| UI |  |  |  |  | 2018-07-21 | 2018-07-22 | 2018-07-17 | 2018-07-23 |  |  |  |  | Xong | 10 | 10
| API |  |  | Catelogy |  | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-30 |  |  |  |  | Xong
|  |  |  | Top Product |  | 2018-07-28 | 2018-07-29 | 2018-07-28 | 2018-07-30 |  |  |  |  | Xong
|  |  |  | Product Detail |  | 2018-07-30 | 2018-07-31 | 2018-07-30 | 2018-07-31 |  |  |  |  | Xong
|  |  |  | Cart |  | 2018-07-30 | 2018-07-31 | 2018-07-31 | 2018-08-01 |  |  |  |  | Xong
|  |  | AsyncStorage |  |  | 2018-07-28 | 2018-07-30 | 2018-07-31 | 2018-08-01 |  |  |  |  | Xong
Note on S9: Input Start date of schedule

## Setting
Holidays
No. | Day | Note
1 | 2018-09-02 | Quốc khánh
2 |  |  | 8 | Plan | 8 | Actual | 30 | Current Date
3
4 |  |  |  | 0-99% |  | 100% |  | Saturday
5
6 |  |  | ◇ | Not yet | △ | Open |  | Sunday, Holiday
7
8 |  |  | ★ | finish over | ○ | Done
9
10 |  |  | ▲ | start over
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100